## Sheet1
Date	Use Case Number(s)	Functionality
Feb 26th	5, 6, 21, 22	At this point we should be able to make a new TopLevelComment and we should be able to browse
		TopLevelComments. There does not have to be ElasticSearch funcitonality. We will mock the
		functionality of the WebServiceController through the CommentController. Unsure if we should
		have location functionality at this point. Probably not.

March 1st	7, 8, 9,	At this point we should also be able to reply to comments, view replies and attach picture to the
		Comment.

March 4th	1, 2, 3, 4	We are expecting sort view functionality at this point.

March 6th	10, 11, 12, 13, 14,	We expect the caches to be implemented by now. Also allow for editing Comments

March 9th	n/a	Clean up ran on wiki. Updates to UML diagram(s).

March 10th	n/a	Project 3 due.

March 17th	18, 19	We expect the location functionality to be implemented by now.

April 7th	15, 16, 17, 20	At this stage we want to ensure that the WebServiceController is fully implemented.

April 9th	n/a	Wiki is in fully presentable state and all appropriate pages are fully edited. Possible YouTube
		video presentation created.

April 10th	n/a	Project 4 due